## Product Burndown
Time (person-hours (p-h))
Sprint | Average Expectation | Ideal Remaining | Planned Remaining | Planned Effort | Actual Effort | Added Requirements | Estimated Remaining
Start |  | 143 | 143 | 0 | 0 | 0 | 143
1 | 18 | 125 | 129 | 14 | 16 | 0 | 127
2 | 18 | 107 | 118 | 9 | 32 | 0 | 118
3 | 18 | 89 | 88 | 30 | 40 | 0 | 88
4 | 18 | 71 | 66.5 | 21.5 | 53.5 | 0 | 66.5
5 | 18 | 53 | 27.5 | 39
6 | 18 | 35
7 | 18 | 17
8 | 17 | 0
Note on G2: Author: requirements added during the sprint that are not from the backlog (estimated hours)

## Sp1
|  |  |  | Week 1 | [5 empty] | Week 2
|  | Date |  | 2014-10-27 | 2014-10-28 | 2014-10-29 | 2014-10-30 | 2014-10-31 | 2014-11-01 | 2014-11-02 | 2014-11-03 | 2014-11-04 | 2014-11-05 | 2014-11-06 | 2014-11-07
|  | Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| Backlog Item | Task | Estimated | [12 empty] | Total Effort
Estimated Planned Effort | 2 | Research Web API's | 6 | 1 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 6
|  | Bryan | 2 | [12 empty] | 2 | bar: 2014-10-27 to 2014-11-07
|  | Dan | 2 | 2014-11-02: 2 | 2
|  | Zach | 2 | [12 empty] | 2 | bar: 2014-10-27 to 2014-11-07
|  | Parse Weather Data | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 3
|  | Bryan | [13 empty] | 0
|  | Dan | 3 | 2014-11-02: 1; 2014-11-03: 2 | 3
|  | Zach | [13 empty] | 0
|  | Calculate Evaporation Rate | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
|  | Bryan | [13 empty] | 0
|  | Dan | [13 empty] | 0
|  | Zach | 1 | [12 empty] | 1 | bar: 2014-10-27 to 2014-11-07
| 3 | Pull Data from NOAA | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 4
|  | Bryan | 4 | 2014-11-01: 1; 2014-11-02: 3 | 4
|  | Dan | [13 empty] | 0
|  | Zach | [13 empty] | 0
Added |  | Create Graph | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5
|  | Bryan | [13 empty] | 0
|  | Dan | 5 | 2014-11-03: 5 | 5
|  | Zach | [13 empty] | 0
| Total: |  | 19 | 1 | 0 | 0 | 0 | 1 | 1 | 9 | 7 | 0 | 0 | 0 | 0 | 19
Estimated Working Effort | 2 | Research Web API's | 6 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75
|  | Bryan | 2 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25
|  | Dan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | Zach | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
|  | Parse Weather Data | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Bryan
|  | Dan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Zach
|  | Calculate Evaporation Rate | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5
Bryan
Dan
|  | Zach | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5
| 3 | Pull Data from NOAA | 4 | 4 | 4 | 4 | 4 | 4 | 2 | -2 | -2 | -2 | -2 | -2 | -2
|  | Bryan | 4 | 4 | 4 | 4 | 4 | 4 | 2 | -2 | -2 | -2 | -2 | -2 | -2
Dan
Zach
Added |  | Create Graph | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0
Bryan
|  | Dan | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0
Zach
| Total: |  | 19 | 18.25 | 18.25 | 18.25 | 18.25 | 18.25 | 16.25 | 8.75 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25
|  |  | 19 | 17.5385 | 16.0769 | 14.6154 | 13.1538 | 11.6923 | 10.2308 | 8.7692 | 7.3077 | 5.8462 | 4.3846 | 2.9231 | 1.4615

## Sp2
|  |  |  | Week 1 |  |  |  |  | Week 2
|  |  | Date | 2014-12-02 | 2014-12-03 | 2014-12-04 | 2014-12-05 | 2014-12-06 | 2014-12-07 | 2014-12-08 | 2014-12-09 | 2014-12-10
|  |  | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
| Backlog Item | Task | Estimated | [9 empty] | Total Effort
Estimated Planned Effort | 1 | Add colors to graph background | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
|  | Bryan | [10 empty] | 0
|  | Dan | 2 |  |  |  |  | 2 |  |  |  |  | 2
|  | Zach | [10 empty] | 0
| 4, 5, and 8 | Add option for inputing concrete temp | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
|  | Bryan | 1 | [5 empty] | 1 |  |  |  | 1
|  | Dan | [10 empty] | 0
|  | Zach | [10 empty] | 0
|  | Show weather variables when hovering over a point and add metric | 6 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 6
|  | Bryan | 3 |  |  |  | 1 | 2 |  |  |  |  | 3
|  | Dan | 3 | [5 empty] | 3 |  |  |  | 3
|  | Zach | [10 empty] | 0
Added |  | Improve input and output UI | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 4
|  | Bryan | 2 | [5 empty] | 2 |  |  |  | 2
|  | Dan | 2 |  |  |  |  | 2 |  |  |  |  | 2
|  | Zach | [10 empty] | 0
|  | Validation for Zip Code | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
|  | Bryan | [10 empty] | 0
|  | Dan | 1 | [5 empty] | 1 |  |  |  | 1
|  | Zach | [10 empty] | 0
| Total: |  | 14 | 0 | 0 | 0 | 1 | 6 | 7 | 0 | 0 | 0 | 14
Estimated Planned Effort | 1 | Add colors to graph background | 2 | 2 | -2 | -2 | -2 | -6 | -8 | -8 | -8 | -8
|  | Bryan | 0
|  | Dan | 2 | 2 | -2 | -2 | -2 | -6 | -8 | -8 | -8 | -8
|  | Zach | 0
| 4, 5, and 8 | Add option for inputing concrete temp | 1 | 1 | 1 | 1 | 1 | 0.5 | -1 | -1 | -1 | -1
|  | Bryan | 1 | 0 | 0 | 0 | 0 | -0.5 | -2 | -2 | -2 | -2
|  | Dan | 0
|  | Zach | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Show weather variables when hovering over a point and add metric | 6 | 6 | 6 | 6 | 6 | 6 | -2 | -2 | -2 | -2
|  | Bryan | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 1.5 | 1.5 | 1.5
|  | Dan | 3 | 3 | 3 | 3 | 3 | 3 | -3.5 | -3.5 | -3.5 | -3.5
|  | Zach | 0
Added |  | Improve input and output UI | 4 | 4 | 4 | 4 | 4 | -1.5 | -6.5 | -6.5 | -6.5 | -6.5
|  | Bryan | 2 | 2 | 2 | 2 | 2 | -3.5 | -3.5 | -3.5 | -3.5 | -3.5
|  | Dan | 2 | 2 | 2 | 2 | 2 | 2 | -3 | -3 | -3 | -3
|  | Zach | 0
|  | Validation for Zip Code | 1 | 1 | 1 | 1 | 1 | 1 | -0.5 | -0.5 | -0.5 | -0.5
|  | Bryan | 0
|  | Dan | 1 | 0 | 0 | 0 | 0 | 0 | -1.5 | -1.5 | -1.5 | -1.5
|  | Zach | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Total: |  | 14 | 14 | 10 | 10 | 10 | 0 | -18 | -18 | -18 | -18
|  |  | 14 | 12.4444 | 10.8889 | 9.3333 | 7.7778 | 6.2222 | 4.6667 | 3.1111 | 1.5556 | 0

## Sp3
|  |  |  | Week 1 | [6 empty] | Week 2
|  |  | Date | 2015-01-18 | 2015-01-19 | 2015-01-20 | 2015-01-21 | 2015-01-22 | 2015-01-23 | 2015-01-24 | 2015-01-25 | 2015-01-26 | 2015-01-27 | 2015-01-28 | 2015-01-29 | 2015-01-30 | 2015-01-31
|  |  | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| Backlog Item | Task | Estimated | [14 empty] | Total Estimated Effort
Estimated Planned Effort | 12 | Create Users table | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
|  | Bryan | [15 empty] | 0
|  | Dan | [15 empty] | 0
|  | Zach | 1.5 |  |  |  | 1.5 | [10 empty] | 1.5
| 15 | Create Users table class | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 1.5
|  | Bryan | [15 empty] | 0
|  | Dan | [15 empty] | 0
|  | Zach | 1.5 | [10 empty] | 1.5 |  |  |  | 1.5
| 21 | Implement User Login and sessions | 8 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 8
|  | Bryan | 8 | [5 empty] | 2 | 2 | [5 empty] | 4 |  | 8
|  | Dan | [15 empty] | 0
|  | Zach | [15 empty] | 0
| 18 | Implement Password security hashing | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
|  | Bryan | 3 |  |  |  |  | 3 | [9 empty] | 3
|  | Dan | [15 empty] | 0
|  | Zach | [15 empty] | 0
| 24, 30 | Format graph points | 8 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
|  | Bryan | [15 empty] | 0
|  | Dan | 8 |  |  | 4 | 4 | [10 empty] | 8
|  | Zach | [15 empty] | 0
| 25, 27, 29 | Format graph | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  | Bryan | [15 empty] | 0
|  | Dan | 5 |  |  |  |  | 5 | [9 empty] | 5
|  | Zach | [15 empty] | 0
| 31 | Implement suggestions to lower evap rate | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
|  | Bryan | [15 empty] | 0
|  | Dan | 3 | [6 empty] | 3 | [7 empty] | 3
|  | Zach | [15 empty] | 0
Added |  | Research new graph libraries | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  | Bryan | [15 empty] | 0
|  | Dan | 2 | 2 | [13 empty] | 2
|  | Zach | [15 empty] | 0
|  | Recreate graph with new library | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
|  | Bryan | [15 empty] | 0
|  | Dan | 6 |  | 6 | [12 empty] | 6
|  | Zach | [15 empty] | 0
| Total: |  | 38 | 2 | 6 | 4 | 5.5 | 8 | 2 | 5 | 0 | 0 | 0 | 1.5 | 0 | 4 | 0 | 38
Estimated Planned Effort | 12 | Create Users table | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Bryan | 0
|  | Dan | 0
|  | Zach | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| 15 | Create Users table class | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | -3.25 | -6 | -6.5 | -6.5
|  | Bryan | 0
|  | Dan | 0
|  | Zach | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | -3.25 | -6 | -6.5 | -6.5
| 21 | Implement User Login and sessions | 8 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bryan | 8 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dan | 0
|  | Zach | 0
| 18 | Implement Password security hashing | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | -1 | -1 | -1 | -1 | -1 | -1
|  | Bryan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | -1 | -1 | -1 | -1 | -1 | -1
|  | Dan | 0
|  | Zach | 0
| 24, 30 | Format graph points | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0.5
|  | Bryan | 0
|  | Dan | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0.5
|  | Zach | 0
| 25, 27, 29 | Format graph | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3.5
|  | Bryan | 0
|  | Dan | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3.5
|  | Zach | 0
| 31 | Implement suggestions to lower evap rate | 3 | 3 | 3 | 2 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1
|  | Bryan | 0
|  | Dan | 3 | 3 | 3 | 2 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1
|  | Zach | 0
Added |  | Research new graph libraries | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Bryan | 0
|  | Dan | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Zach | 0
|  | Recreate graph with new library | 6 | 6 | 2 | -3 | -3 | -3 | -3 | -3 | -3 | -3 | -3 | -3 | -3 | -3 | -3
|  | Bryan | 0
|  | Dan | 6 | 6 | 2 | -3 | -3 | -3 | -3 | -3 | -3 | -3 | -3 | -3 | -3 | -3 | -3
|  | Zach | 0
| Total: |  | 17.5 | 17.5 | 12.5 | 6.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1
|  |  | 17.5 | 16.25 | 15 | 13.75 | 12.5 | 11.25 | 10 | 8.75 | 7.5 | 6.25 | 5 | 3.75 | 2.5 | 1.25 | 0

## Sp4
|  |  |  | Week 1 | [6 empty] | Week 2
|  |  | Date | 2015-03-01 | 2015-03-02 | 2015-03-03 | 2015-03-04 | 2015-03-05 | 2015-03-06 | 2015-03-07 | 2015-03-08 | 2015-03-09 | 2015-03-10 | 2015-03-11 | 2015-03-12 | 2015-03-13 | 2015-03-14
|  |  | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| Backlog Item | Task | Estimated | [14 empty] | Total Estimated Effort
Estimated Planned Effort | 28 | Create About Page | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
|  | Bryan | 2 | [10 empty] | 2 |  |  |  | 2
|  | Dan | [15 empty] | 0
|  | Zach | [15 empty] | 0
| 16 | Create Forgot Password Page | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
|  | Bryan | 2 | [9 empty] | 2 |  |  |  |  | 2
|  | Dan | [15 empty] | 0
|  | Zach | [15 empty] | 0
| 9 | Implement service for city, state, timezone info | 8 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 8
|  | Bryan | 4 | [8 empty] | 4 | [5 empty] | 4
|  | Dan | 4 |  | 4 | [12 empty] | 4
|  | Zach | [15 empty] | 0
| 6, 7, 19 | Implement Database Interaction Classes | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
|  | Bryan | [15 empty] | 0
|  | Dan | [15 empty] | 0
|  | Zach | 4 | [13 empty] | 4 | 4
| 17, 22 | Bug Fixes | 5.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 5.5
|  | Bryan | 2 | [12 empty] | 2 |  | 2
|  | Dan | 3.5 |  | 3.5 | [12 empty] | 3.5
|  | Zach | [15 empty] | 0
Added |  | Create Projects Page | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
|  | Bryan | 2 | [9 empty] | 2 |  |  |  |  | 2
|  | Dan | [15 empty] | 0
|  | Zach | [15 empty] | 0
|  | Create the Create Account Page | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
|  | Bryan | 2 | [9 empty] | 2 |  |  |  |  | 2
|  | Dan | [15 empty] | 0
|  | Zach | [15 empty] | 0
|  | Various formatting fixes | 10 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 10
|  | Bryan | 2 | [11 empty] | 2 |  |  | 2
|  | Dan | 8 |  |  |  | 8 | [10 empty] | 8
|  | Zach | [15 empty] | 0
|  | Change times to account for timezones | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
|  | Bryan | 2 | [10 empty] | 2 |  |  |  | 2
|  | Dan | [15 empty] | 0
|  | Zach | [15 empty] | 0
|  | Change windspeed functionality | 4.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5
|  | Bryan | [15 empty] | 0
|  | Dan | 4.5 | 2.5 | [5 empty] | 2 | [7 empty] | 4.5
|  | Zach | [15 empty] | 0
|  | Research | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  | Bryan | 2 | [7 empty] | 2 | [6 empty] | 2
|  | Dan | [15 empty] | 0
|  | Zach | [15 empty] | 0
| Total: |  | 44 | 2.5 | 7.5 | 0 | 8 | 0 | 0 | 2 | 2 | 4 | 6 | 4 | 2 | 2 | 4 | 44
Estimated Planned Effort | 28 | Create About Page | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
|  | Bryan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
|  | Dan | 0
|  | Zach | 0
| 16 | Create Forgot Password Page | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1
|  | Bryan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1
|  | Dan | 0
|  | Zach | 0
| 9 | Implement service for city, state, timezone info | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4.25 | 4.25 | 4.25
|  | Bryan | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0.5 | 0.5 | 0.5
|  | Dan | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3.75 | 3.75 | 3.75
|  | Zach | 0
| 6, 7, 19 | Implement Database Interaction Classes | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | -4
|  | Bryan | 0
|  | Dan | 0
|  | Zach | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | -4
| 17, 22 | Bug Fixes | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 4.5 | 1.5 | 1.5 | 1.5 | 0.5 | -4.5
|  | Bryan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | -2 | -2 | -2 | -3 | -4
|  | Dan | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | -0.5
|  | Zach | 0
Added |  | Create Projects Page | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
|  | Bryan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
|  | Dan | 0
|  | Zach | 0
|  | Create the Create Account Page | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
|  | Bryan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
|  | Dan | 0
|  | Zach | 0
|  | Various formatting fixes | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 7.5 | 4.5 | -1
|  | Bryan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | -1 | -2
|  | Dan | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7.5 | 5.5 | 1
|  | Zach | 0
|  | Change times to account for timezones | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | -3.5 | -6 | -6
|  | Bryan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Dan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.5 | -6 | -6
|  | Zach | 0
|  | Change windspeed functionality | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 3 | 1.75
|  | Bryan | 0
|  | Dan | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 3 | 1.75
|  | Zach | 0
|  | Research | 2 | 2 | 2 | 2 | 2 | -2 | -2 | -2 | -2 | -4 | -4 | -4 | -4 | -4 | -4
|  | Bryan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dan | 0 | 0 | 0 | 0 | 0 | -4 | -4 | -4 | -4 | -4 | -4 | -4 | -4 | -4 | -4
|  | Zach | 0
| Total: |  | 44 | 44 | 44 | 44 | 44 | 40 | 40 | 40 | 40 | 37 | 31 | 31 | 21.25 | 10.25 | -9.5
|  |  | 44 | 40.8571 | 37.7143 | 34.5714 | 31.4286 | 28.2857 | 25.1429 | 22 | 18.8571 | 15.7143 | 12.5714 | 9.4286 | 6.2857 | 3.1429 | -4.4409e-15

## Sp5
|  |  |  | Week 1 | [6 empty] | Week 2
|  |  | Date | 2015-03-16 | 2015-03-17 | 2015-03-18 | 2015-03-19 | 2015-03-20 | 2015-03-21 | 2015-03-22 | 2015-03-23 | 2015-03-24 | 2015-03-25 | 2015-03-26 | 2015-03-27 | 2015-03-28 | 2015-03-29
|  |  | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| Backlog Item | Task | Estimated | [14 empty] | Total Estimated Effort
Estimated Planned Effort | 28, 29, 30, 31, 33 | Format Graph | 4 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  | Bryan | 1 | 1 | [13 empty] | 1
|  | Dan | 3 |  |  |  |  | 3 | [9 empty] | 3
|  | Zach | [15 empty] | 0
| 26 | Design Pages | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3
|  | Bryan | 2 | [12 empty] | 2 |  | 2
|  | Dan | 1 | [12 empty] | 1 |  | 1
|  | Zach | [15 empty] | 0
| 26 | Finish Database Interaction Classes | 25 | 0 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 25
|  | Bryan | 10 | [5 empty] | 5 | [6 empty] | 5 |  | 10
|  | Dan | [15 empty] | 0
|  | Zach | 15 |  |  | 5 |  | 5 |  |  |  |  | 5 |  |  |  |  | 15
| 32, 34 | Add functionality to graph | 7 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
|  | Bryan | [15 empty] | 0
|  | Dan | 7 |  |  | 4 | 3 | [10 empty] | 7
|  | Zach | [15 empty] | 0
Added |  | Testing | 12 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 12
|  | Bryan | 5 | [13 empty] | 5 | 5
|  | Dan | 3 | [13 empty] | 3 | 3
|  | Zach | 4 | [5 empty] | 2 | [6 empty] | 2 |  | 4
|  | Server Setup | 15 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
|  | Bryan | 5 | 3 |  | 2 | [11 empty] | 5
|  | Dan | 5 | 3 | 2 | [12 empty] | 5
|  | Zach | 5 | 3 | 2 | [12 empty] | 5
| Total: |  | 66 | 10 | 4 | 11 | 3 | 8 | 7 | 0 | 0 | 0 | 5 | 0 | 0 | 10 | 8 | 66
Estimated Planned Effort | 12 | Create Users table | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bryan | 1
|  | Dan | 3
|  | Zach | 0
| 15 | Create Users table class | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bryan | 2
|  | Dan | 1
|  | Zach | 0
| 21 | Implement User Login and sessions | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bryan | 10
|  | Dan | 0
|  | Zach | 15
| 18 | Implement Password security hashing | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bryan | 0
|  | Dan | 7
|  | Zach | 0
| 24, 30 | Format graph points | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bryan | 5
|  | Dan | 3
|  | Zach | 4
Added | 25, 27, 29 | Format graph | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bryan | 5
|  | Dan | 5
|  | Zach | 5
| 31 | Implement suggestions to lower evap rate | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bryan | #REF!
|  | Dan | #REF!
|  | Zach | #REF!
|  | Research new graph libraries | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bryan | #REF!
|  | Dan | #REF!
|  | Zach | #REF!
|  | Recreate graph with new library | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bryan | #REF!
|  | Dan | #REF!
|  | Zach | #REF!
| Total: |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!