## Sp5
No. | Risk | Likelihood | Impact | Score | Mitigation Strategy | Contingency Plan

## Sp4
No. | Risk | Likelihood | Impact | Score | Mitigation Strategy | Contingency Plan
4 | fail to meet deadlines | 4 | 8 | 32 | try to space our milestones out in a way that gives us enough time complete them, meet at least once a week to make sure everyone is on track | re-evaluate our milestones and adjust them
6 | customer adds requirements | 5 | 4 | 20 | get all the requirements beforehand and add it to the process spec | change the process spec and project plan to account for new requirements
8 | host server goes down | 2 | 6 | 12 | N/A | Use backup server until main server comes back up

## Sp3
No. | Risk | Likelihood | Impact | Score | Mitigation Strategy | Contingency Plan
1 | no prior security knowledge | 10 | 10 | 100 | N/A | Learn security
4 | fail to meet deadlines | 4 | 8 | 32 | try to space our milestones out in a way that gives us enough time complete them, meet at least once a week to make sure everyone is on track | re-evaluate our milestones and adjust them
6 | customer adds requirements | 5 | 4 | 20 | get all the requirements beforehand and add it to the process spec | change the process spec and project plan to account for new requirements
8 | host server goes down | 2 | 6 | 12 | N/A | Use backup server until main server comes back up
9 | NOAA permenantly goes offline | 1 | 10 | 10 | write code with low coupling so that it is easily able to use another weather API | Find a different weather service
10 | Project data gets lost | 1 | 10 | 10 | store on our local computers in addition to using bitbucket | reupload latest version we have to minimize lost work
11 | lose a team member | 1 | 8 | 8 | follow SAGE process spec | redistribute tasks and workload

## Sp2
No. | Risk | Likelihood | Impact | Score | Mitigation Strategy | Contingency Plan
1 | no prior security knowledge | 10 | 10 | 100 | N/A | Learn security
3 | website is not user friendly | 5 | 7 | 35 | perform usability study | take results from usability study and improve UI
4 | fail to meet deadlines | 4 | 8 | 32 | try to space our milestones out in a way that gives us enough time complete them, meet at least once a week to make sure everyone is on track | re-evaluate our milestones and adjust them
6 | customer adds requirements | 5 | 4 | 20 | get all the requirements beforehand and add it to the process spec | change the process spec and project plan to account for new requirements
7 | cannot get siue email for notification service | 4 | 4 | 16 | trying now to get one from ITS | use a free account from another email service
8 | host server goes down | 2 | 6 | 12 | N/A | Use backup server until main server comes back up
9 | NOAA permenantly goes offline | 1 | 10 | 10 | write code with low coupling so that it is easily able to use another weather API | Find a different weather service
10 | Project data gets lost | 1 | 10 | 10 | store on our local computers in addition to using bitbucket | reupload latest version we have to minimize lost work
11 | lose a team member | 1 | 8 | 8 | follow SAGE process spec | redistribute tasks and workload

## Sp1
No. | Risk | Likelihood | Impact | Score | Mitigation Strategy | Contingency Plan
1 | no prior security knowledge | 10 | 10 | 100 | N/A | Learn security
2 | Limited Web API knowledge | 10 | 9 | 90 | N/A | Learn Web API
3 | website is not user friendly | 5 | 7 | 35 | perform usability study | take results from usability study and improve UI
4 | fail to meet deadlines | 4 | 8 | 32 | try to space our milestones out in a way that gives us enough time complete them, meet at least once a week to make sure everyone is on track | re-evaluate our milestones and adjust them
6 | customer adds requirements | 5 | 4 | 20 | get all the requirements beforehand and add it to the process spec | change the process spec and project plan to account for new requirements
7 | cannot get siue email for notification service | 4 | 4 | 16 | trying now to get one from ITS | use a free account from another email service
8 | host server goes down | 2 | 6 | 12 | N/A | Use backup server until main server comes back up
9 | NOAA permenantly goes offline | 1 | 10 | 10 | write code with low coupling so that it is easily able to use another weather API | Find a different weather service
10 | Project data gets lost | 1 | 10 | 10 | store on our local computers in addition to using bitbucket | reupload latest version we have to minimize lost work
11 | lose a team member | 1 | 8 | 8 | follow SAGE process spec | redistribute tasks and workload

## Orig
No. | Risk | Likelihood | Impact | Score | Mitigation Strategy | Contingency Plan
1 | no prior security knowledge | 10 | 10 | 100 | N/A | Learn security
2 | Limited Web API knowledge | 10 | 9 | 90 | N/A | Learn Web API
3 | website is not user friendly | 5 | 7 | 35 | perform usability study | take results from usability study and improve UI
4 | fail to meet deadlines | 4 | 8 | 32 | try to space our milestones out in a way that gives us enough time complete them, meet at least once a week to make sure everyone is on track | re-evaluate our milestones and adjust them
5 | cannot get server from ITS | 4 | 6 | 24 | trying now to get one from ITS | find a different server host
6 | customer adds requirements | 5 | 4 | 20 | get all the requirements beforehand and add it to the process spec | change the process spec and project plan to account for new requirements
7 | cannot get siue email for notification service | 4 | 4 | 16 | trying now to get one from ITS | use a free account from another email service
8 | host server goes down | 2 | 6 | 12 | N/A | Use backup server until main server comes back up
9 | NOAA permenantly goes offline | 1 | 10 | 10 | write code with low coupling so that it is easily able to use another weather API | Find a different weather service
10 | Project data gets lost | 1 | 10 | 10 | store on our local computers in addition to using bitbucket | reupload latest version we have to minimize lost work
11 | lose a team member | 1 | 8 | 8 | follow SAGE process spec | redistribute tasks and workload