## Sprint Backlog
Sprint Backlog
| ID | Priority | Tasks | Week 1 Estimated Time | Week 2 Estimated Time | Work Remaining
| 1 | 1 | Research Web Services and API's | 6 | 0 | 0
|  |  | Bryan | 2 |  | 0
|  |  | Daniel | 2 |  | 2
|  |  | Zach | 2 |  | 2
| 2 | 2 | Pull weather data from NOAA | 0 | 4 | 0
|  |  | Bryan |  | 4 | 0
| 3 | 4 | Output evaporation date in a line graph | 0 | 4 | 0
|  |  | Daniel |  | 4 | 0
| 4 | 3 | Create function to calculate evaporation rate | 0 | 1 | 0
|  |  | Zach |  | 1 | 0
|  |  | Total | 6 | 9 | 0
Note: parse weather data from tasks is part of pull weather data from NOAA…. and added Output evaporation date in a line graph.

## Team Sprint Burndown Chart
Sprint Burndown
| Week | 0 | 1 | 2
| Estimated Hours Left | 15 | 9 | 0
Actual Hours Left

## Daniel Sprint Burndown
Sprint Burndown
| Week | 0 | 1 | 2
| Estimated Hours Left | 6 | 4 | 0
Actual Hours Left

## Bryan Sprint Burndown
Sprint Burndown
| Week | 0 | 1 | 2
| Estimated Hours Left | 6 | 4 | 0
Actual Hours Left

## Zach Sprint Burndown
Sprint Burndown
| Week | 0 | 1 | 2
| Estimated Hours Left | 3 | 1 | 0
Actual Hours Left